## Sheet1
[10 empty] | Low | Medium | High
Risk Register for Project FixFlow
Risk ID | Category | Title | Description | Potential Impact | Impact Rating (1-10) | Probability (1-10) | Risk Score (impact * probability) | Rank | Mitigation plan
R-01 | Technical | Integration Issues | Lack of alignment in data structure. For example, the server returns an object (dictionary) while the client expects an Array. | Critical client-side errors that prevent users from performing basic Actions. | 9 | 6 | 54 | 2 | Create detailed API Documentation.
R-02 | Resource | Frontend–Backend integration Delays | Delay in connecting frontend components with backend API endpoints, causing incomplete system functionality during the sprint | Blocks feature completion and slows overall progress, especially for login and issue management Flows | 8 | 8 | 64 | 1 | Use mock data and perform incremental integration once backend endpoints are stable
R-03 | Technical | Authentication / API Errors | Issues with login or authentication endpoints may prevent users from accessing the system properly | Prevents system usage and testing of core features like issue creation and tracking | 10 | 4 | 40 | 3 | Test endpoints independently (e.g., Postman), debug authentication flow, and isolate issues before integration
R-04 | Timeline | Incomplete Sprint 2 Features | Some user stories (e.g., issue viewing, opening issues) remain unfinished due to time constraints | Reduces MVP completeness and affects demo quality | 6 | 6 | 36 | 4 | Prioritize “Must” features and defer less critical tasks (MoSCoW method)
R-05 | Reputational | Stale and Non-Uniform Data | Relying on local SQLite databases results in fragmented and "stale" data across different developers' local machines. | Inconsistent testing environments, leading to integration failures and masked bugs During Frontend – Backend Synchronization. | 4 | 5 | 20 | 5 | Deploy a centralized MySQL database to establish a single source of truth and uniform real-time data for the entire team.
| Total Risk Score |  | 214 | 0 |  | Project Risk Rating |  |  | Medium